## FuzzAIoT
Sprint-wise Retrospective
AI - Driven Fuzz Testing for IoT Security
Product Category: Research
Sprint 1 : Setup NS3 Simulation Environment
Liked | Learned | Lacked | Longed For
Share aspects of the sprint that you enjoyed or found particularly effective. | Discuss lessons learned, whether they are related to processes, technical aspects, or teamwork. | Identify areas where the team felt a lack of resources, support, or information. | Discuss any desires or expectations that the team had but were not met during the sprint.
Successfully set up the NS3 environment without any major errors. | Learned the nuances of configuring an IoT network in NS3. | Lacked sufficient examples for simulating complex IoT devices. | Desired more efficient methods for configuring and simulating diverse IoT environments.
Collaboration between network engineers and data scientists led to efficient environment configuration. | Gained insights into how network simulations can generate valuable data for GNN model training. | Missing support for advanced network configurations out-of-the-box in NS3. | Wished for a more integrated system for logging and analyzing simulation data.
The initial IoT network topology was established smoothly. | Discovered best practices for organizing simulation files and settings. | Faced delays due to a lack of clear guidelines for generating XML traffic logs. | Hoped for additional modules in NS3 for simulating real-time network behavior.
Realistic traffic generation was accurate as per simulation requirements. | Enhanced knowledge on the limitations of default NS3 modules and the need for customization. | Insufficient time was allocated for testing the simulation setup under various scenarios. | Longed for more structured sprint planning and resource allocation to avoid last-minute rushes.
Detailed documentation was well-structured and comprehensive. | Understood the importance of proper testing procedures in simulation environments. | More powerful computing resources would have made simulation faster. | Desired quicker feedback from the testing phase, as it took longer than anticipated.
Sprint 2 : Generate Dataset for GNN Training
Liked | Learned | Lacked | Longed For
Share aspects of the sprint that you enjoyed or found particularly effective. | Discuss lessons learned, whether they are related to processes, technical aspects, or teamwork. | Identify areas where the team felt a lack of resources, support, or information. | Discuss any desires or expectations that the team had but were not met during the sprint.
The dataset was successfully extracted and processed for model training. | Gained experience in transforming raw simulation data into useful training datasets. | Lack of real-world IoT traffic patterns limited the diversity of the dataset. | Wanted more detailed simulation logs with additional network parameters.
Collaboration between network engineers and data scientists improved data quality. | Understood the importance of balancing datasets to avoid model bias. | Insufficient feature documentation slowed down the feature engineering process. | Desired automated tools to expedite data extraction and cleaning processes.
Feature engineering helped in deriving relevant insights from the simulation logs. | Learned how to extract relevant features (e.g., timestamps, packet sizes) for GNN training. | Limited access to automated tools for dataset balancing. | Hoped for easier integration of external data sources for richer training datasets.
Preprocessing steps ensured that the dataset was well-balanced and usable. | Realized the necessity of ensuring dataset consistency for effective model performance. | Lacked predefined templates for preprocessing and feature extraction. | Wished for more comprehensive test datasets to check the feature quality.
Documentation of the data extraction and preprocessing steps was clear and concise. | Explored techniques for handling missing data in network traffic logs. | More team communication was needed during the dataset validation process. | Desired quicker feedback cycles from the data validation phase to avoid bottlenecks.
Sprint 3 : Train GNN Model for DDoS Detection
Liked | Learned | Lacked | Longed For
Share aspects of the sprint that you enjoyed or found particularly effective. | Discuss lessons learned, whether they are related to processes, technical aspects, or teamwork. | Identify areas where the team felt a lack of resources, support, or information. | Discuss any desires or expectations that the team had but were not met during the sprint.
The model training process was smooth, and early results were promising. | Understood the impact of hyperparameters on GNN performance. | Lacked real-time evaluation during the model testing phase. | Wanted faster results from hyperparameter tuning using better computational resources.
Team collaboration improved during hyperparameter tuning efforts. | Learned techniques to fine-tune the model for different network traffic patterns. | Limited computational power made the hyperparameter tuning slow. | Desired real-time traffic to test the model on live data.
Reached the target accuracy of 75% on the validation set. | Gained experience in handling large datasets during model training. | Faced challenges in finding optimal learning rates and other parameters. | Hoped for a more intuitive visualization of model performance over time.
The GNN model was able to classify DDoS traffic effectively. | Explored how GNN architectures can be customized for IoT traffic analysis. | Needed more test data with various DDoS attack patterns for robust training. | Wished for better tools to automate model performance monitoring.
Good progress was made in documenting model architecture and training procedures. | Realized the importance of validation in reducing overfitting during training. | Lack of comprehensive documentation on hyperparameter tuning strategies. | Desired quicker model validation feedback to avoid prolonged tuning cycles.
Sprint 4 : Implement Real-Time DDoS Mitigation in NS3
Liked | Learned | Lacked | Longed For
Share aspects of the sprint that you enjoyed or found particularly effective. | Discuss lessons learned, whether they are related to processes, technical aspects, or teamwork. | Identify areas where the team felt a lack of resources, support, or information. | Discuss any desires or expectations that the team had but were not met during the sprint.
Successfully integrated the GNN model with NS3 for real-time mitigation. | Learned how to integrate a GNN model within a network simulation environment. | Lacked real-time logging tools to monitor the mitigation process more effectively. | Desired quicker ways to simulate different types of DDoS attacks in NS3.
The packet filtering mechanism worked as expected to block malicious traffic. | Gained insights into real-time packet filtering and its effects on network performance. | Required more comprehensive test cases to validate the mitigation strategy under varied conditions. | Wished for more advanced visualization tools to monitor traffic in real-time.
Team communication was efficient during the integration and testing phases. | Understood the importance of balancing security measures with network throughput. | Lacked sufficient documentation on integrating machine learning models in NS3. | Hoped for seamless integration of the mitigation strategy into live network environments.
Network performance was monitored closely, and legitimate traffic was unaffected. | Learned how to implement dynamic filtering based on the model’s predictions. | Faced delays due to insufficient knowledge about real-time packet filtering techniques. | Wanted more advanced packet filtering options that are easily configurable.
Clear documentation of the mitigation strategy helped in replicating the process. | Realized the challenges of maintaining performance while mitigating attacks. | Required more scenarios to fully test the GNN model’s effectiveness in diverse traffic conditions. | Desired more real-world IoT traffic data for more accurate mitigation testing.